## Web_App_Calendar
Defect ID | Area | Summary | Priority | Screenshot | Status | Remarks
WEB-1 | Home Screen | Allow button does not work - in location access pop up [Refer attached screenshot]. Every time user refreshes the load, user gets allow pop up | High | https://drive.google.com/file/d/1FP75234xfE5JKqRld0lGyx25YBM-dLDc/view?usp=sharing | NEW | This is not a bug, its a feature of safari browser. try with another browser and try different website on safari . there is also one option in screenshot to remember the location
WEB-2 | Google Login | Gmail login does not work [Access blocked error is displaying] | Critical | https://drive.google.com/file/d/1nHf3btGliwuPlyTb1v2RqoOCM2UL3glU/view?usp=sharing | Closed | Fixed
WEB-3 | Browse Events | Error "Please complete your profile" error displays on clicking Browse events button. Expected: Browse events can be accessed by guest user also | High | https://drive.google.com/file/d/1oWg7qqhJ63I5Oy2b_6vzXBLJLg5btrk-/view?usp=sharing | Closed | Fixed
WEB-4 | Create Events | Y only Family Event option is displaying ? eventhough there are are more catgeory created in staging admin panel | Critical | https://drive.google.com/file/d/1_jTq-ayLyiGJVxcjptculWneXN3cryqN/view?usp=sharing | Closed | - We have to fetch only language specific category of events. QA Comments: - Yes correct, so I believe now our webapp is pointing to language = MS (Master)
WEB-5 | Create Events | Email Id field is not required in creating social events | High |  | REOPENED | Dharmesh Comment: Fixed Sudeep Comment: - This is not fixed, I still see email field in creating event pop up
WEB-6 | Create Events | Start Time and End Time cannot be picked | Critical | https://drive.google.com/file/d/1wrdP-R-2-OX2BYi-_NIwDwcCzCinewPE/view?usp=sharing | Closed | Fixed
WEB-7 | Create Events | Invite user by gmail - Y again it is asking for organizer to login to gmail ? Since oraganizer is already logged in to gmail to create account | High |  | NEW | This is for security reasons. when we login via google we can/have to fetch only user tokens and profile object. so when he needs to access his contact list, he needs again verify him self via google login.
WEB-8 | Create Events | Not able to create Social Events from web app | Critical |  | REOPENED | Dharmesh Comment: Fixed Sudeep Comment: - This is not fixed, I still see email field in creating event pop up
WEB-9 | Create Events | When attachment is added while creating event, event banner image disappears | Critical |  | NEW
WEB-10 | Create Events | Location service used is not helpful to us - It does not displays city or towns. Only taluk it displays | Critical |  | NEW
WEB-11 | Create Events | Access blocked: exaweb.in has not completed the Google verification process - error displays when user tries to login in during invite user flow while creating social events | High |  | NEW