## Web_App_Calendar
Defect ID | Area | Summary | Priority | Screenshot | Status | Remarks
WEB-1 | Home Screen | Allow button does not work - in location access pop up [Refer attached screenshot]. Every time user refreshes the webapp, user gets allow pop up Note: Issue is also seen when user clicks on Eventz logo button in the web app | High | https://drive.google.com/file/d/1FP75234xfE5JKqRld0lGyx25YBM-dLDc/view?usp=sharing | Reopened | Dharmesh Comments: This is not a bug, its a feature of safari browser. try with another browser and try different website on safari . there is also one option in screenshot to remember the location QA Comments: 1. Not working in safari, Chrome, Firefox
WEB-2 | Google Login | Gmail login does not work [Access blocked error is displaying] | Critical | https://drive.google.com/file/d/1nHf3btGliwuPlyTb1v2RqoOCM2UL3glU/view?usp=sharing | Closed | Fixed
WEB-3 | Browse Events | Error "Please complete your profile" error displays on clicking Browse events button. Expected: Browse events can be accessed by guest user also | High | https://drive.google.com/file/d/1oWg7qqhJ63I5Oy2b_6vzXBLJLg5btrk-/view?usp=sharing | Closed | Fixed
WEB-4 | Create Events | Y only Family Event option is displaying ? eventhough there are are more catgeory created in staging admin panel | Critical | https://drive.google.com/file/d/1_jTq-ayLyiGJVxcjptculWneXN3cryqN/view?usp=sharing | Closed | - We have to fetch only language specific category of events. QA Comments: - Yes correct, so I believe now our webapp is pointing to language = MS (Master)
WEB-5 | Create Events | Email Id field is not required in creating social events | High |  | Closed | Dharmesh Comment: Fixed Sudeep Comment: - This is not fixed, I still see email field in creating event pop up
WEB-6 | Create Events | Start Time and End Time cannot be picked | Critical | https://drive.google.com/file/d/1wrdP-R-2-OX2BYi-_NIwDwcCzCinewPE/view?usp=sharing | Closed | Fixed
WEB-7 | Create Events | Invite user by gmail - Y again it is asking for organizer to login to gmail ? Since oraganizer is already logged in to gmail to create account | High |  | NEW | This is for security reasons. when we login via google we can/have to fetch only user tokens and profile object. so when he needs to access his contact list, he needs again verify him self via google login.
WEB-8 | Create Events | Not able to create Social Events from web app | Critical |  | Closed | Dharmesh Comment: Fixed Sudeep Comment: - This is not fixed, I still see email field in creating event pop up
WEB-9 | Create Events | When attachment is added while creating event, event banner image disappears | Critical |  | Closed
WEB-10 | Create Events | Location service used is not helpful to us - It does not displays city or towns. Only taluk it displays | Critical |  | Closed
WEB-11 | Create Events | Access blocked: exaweb.in has not completed the Google verification process - error displays when user tries to login in during invite user flow while creating social events | High |  | NEW | - Right now google application is in testing. it requires verification process and for that we need App logo , privacy policy page etc etc . check these two links. To get verified by google is long and tedius process https://tinyurl.com/2lra5n2m https://tinyurl.com/2hqru9bm
WEB-12 | Browse Events | Social events seen in web app before it is been approved by admin. Working should be same as that of mobile app | High |  | Closed | This is Fixed
WEB-13 | Event Detail Page | Attachments (Image, audio and file) not seen in event detail page, I created one event in mobile app with attachments added (Image, audio and file). But attachments are not seen in web app event detail page | High |  | NEW | Developer Comment: This is Fixed QC Comment: Cannot verify now, since mobile app is crashing now while creating event with event creation
WEB-14 | Event Detail Page | All invite list : Not displaying in event detail page I created one event in mobile app with 2 invites (Mobile number and registered user). But invite lists are not seen in web app event detail page | High |  | Closed | This is Fixed
WEB-15 | Event Detail Page | Directions : Google map link is not displaying in event detail page I created one event in mobile app. But directions link is missing. Working should be same as that of mobile app | High |  | Closed
WEB-15 | Event Detail Page | Event type (Social / Family etc) badge we need to display in event detail page like how you display public / private event | High |  | Closed
WEB-17 | Event Detail Page | Organizer Details needs to be displayed in web app event detail page, Name Mobile Number Email | High |  | Closed
WEB-18 | Event Detail Page | Address details added during create event does not display in event detail page of web app | High |  | Closed | This is Fixed
WEB-19 | Event Detail Page | Event organiser should not be allowed to set event status, Now even who created event can set event status as Attending or etc | High |  | Closed | This is Fixed
WEB-20 | Event Detail Page | Google map link - redirected does not give result. It says "google map cant find location....." | High |  | Closed | This is Fixed
WEB-21 | Create Events | While uploading Image - jpg is not supported ? Iam not able to upload event image of format jpg | High |  | Closed | This is Fixed
WEB-22 | Edit Events | I cannot see any provision to edit the event in web app. Organiser should be able to edit the event | High |  | Closed | This is Fixed
WEB-23 | Create Events | By default keep Public as first option and let by default public be selected | Medium |  | Closed
WEB-23 | Near by Events | Web app and Mobile app near by events are different , We used below API to display nearby events, https://debug.exaweb.in:3004/api/socialevents?eventStatus=APPROVED&nearBy=true&lat=12.91&long=74.85&distance=300000&language=MS | High |  | Reopened | QA Comments: I cannot see any nearby events even though there is one near by event for location Manglore, Karnataka. I can see in mobile app | Try to test this with newly created event
WEB-24 | Event Detail Page | In mobile app address field is blank, for which the event is created in web app. Please pass the address entered while creating event in in key "address 2" | Medium |  | Closed | This is Fixed
WEB-25 | Near by Events | Near By events are filtered using location, So I suggest to remove location at the top of the site and lets bring in near by events browse events page [We can discuss this in call] | High |  | NEW | Not sure what do you want here. QA Comments: We can discuss in call
WEB-26 | Mange Profile Page | In personal info page, Event category is displayed EMPTY. Event category cannot be empty for any user. Note: I did Sign up in mobile app (selected categpry as social event), and then login in web app, observe that category is empty). | High |  | Reopened | Developer Comment: I did not face this issue. try with new signup or send video / screenshot QA Comment: I did Sign up in mobile app (selected categpry as social event), and then login in web app, observe that category is empty).
WEB-27 | Home Screen | Top tool bar disappears Search, Browse events, create events etc when user does pull down refresh | Medium |  | Reopened | Developer Comment: This is not bug . it is feature . check here https://eventz.clonegranny.com/ QA Comment: This issue is seen only in safari browser
WEB-28 | Create Profile Page | In Create profile page. I observed that location / address is the field where simple texts will be entered. How you can get the coordinate if user enters randomly ? | High |  | Reopened | This is Fixed QA Comment: - Please use same field of mobile app on create profile page - Fields ()
WEB-29 | Create Profile Page | After Profile is created, user is still in create profile page. Expected is to take user to back screen | Medium |  | Closed | This is Fixed
WEB-30 | Events Page | When clicking on "Follow" button from suggested account - it has to be removed from the UI. Now it remains there - looks like refersh issue | Low |  | NEW
WEB-31 | Mobile APP - Login | Mobile App is crashing on login, if we edit event category in web app | High |  | NEW
WEB-32 | Profile Search | Another users Profile detail page : Followers and Following count is not displaying properly. Wrong data displaying | High |  | NEW
WEB-33 | Edit Profile | Edit Profile field should be same as that of mobile app, Mobile App fields: > Profile pic > First Name > Last Name > UserName > Birthday > Select Rashi > Select City / Location > Select Catgeory > Email (non editable if it is email logged in user) > Mobile number Note: Remove extra field and add only the fields used in mobile app | High |  | NEW
WEB-34 | Create Event | Need an provision for user to select the attachment type in the UI, Attachment type: - Image - Audio - File | Medium |  | NEW
WEB-35 | Mobile APP - Create Account | Mobile app is crashing on creating event when all attachments is added | High |  | NEW
WEB-36 | Near by Events | I cannot see any NearBy events in web app UI | High |  | NEW
WEB-37 | Popular Events | I cannot see any Popular events in web app UI | High |  | NEW
WEB-38 | Event Detail Page | Mobile number invited : Mobile number does not dipsplay in Invited user popup . Expected is to display +91 XXX XXX (last 4 digit visible) in event detail page for non created user and display full mobile number for created user | High |  | NEW
WEB-39 | Mobile Browser - Responsive UI | Web app is not user freiendly in mobile browser UI / Responsive UI. | High |  | NEW
WEB-40 | Create Profile Page | Location service used is not helpful to us - It does not displays city or towns. Only taluk it displays | High |  | NEW
WEB-41 | Create Event Page | Uploaded event banner not seen in the UI for below steps: (Go to create event page ----> Upload Banner ----> Now delete banner ----> Again try to uplaod) | Medium |  | NEW